Meeting Agenda – Oct 5, 2014

WEEK 1 (Oct 6 - Oct 12):

**1. mHealth Platform Research**

* Study MOTECH Architecture – platforms, modules, and functionalities
* Study features of COMMCARE and how to best integrate them into MOTECH

**2. Network with mHealth Tech Firms**

* Skype Chat with Medic Mobile on Oct 10 at 11am
* Skype Chat with SANA on Oct 9 at 10:30pm

**3. Other ongoing Projects:**

Development of training content for CHWs

* Content areas – MCH care, newborn care etc.
* Pedagogical methods – workshops, role play, technical training etc.
* Operational aspects – Community Outreach, point of care training, on-site counseling etc.

WEEK 2 (Oct 13 - Oct 19):

1. Develop Road Map for MOTECH Customization

To adapt MOTECH for MCH services in India, we need to figure out use of the following MOTECH features:

* Personalized voice and text messages
* CHW job aids like appointment/task scheduler, on-site counseling support, refresher training course, and CHW assessment tools.
* Data keeping via open MRS
* Development and deployment of care plans, clinical protocols, and decision-support tools
* Integration of telemedicine modules/functionalities into MOTECH
* Interoperability between different components and ensuring scalability to different health areas like heart care, diabetic care etc.